## Ark1
| PLAN |  |  |  |  | DESIGN |  |  |  |  | BUILD |  |  |  |  | LAUNCH
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
PROJECT MANAGER | PROJECT MANAGEMENT AND CONTRACT |  |  |  |  | PROJECT MANAGEMENT |  |  |  |  | PROJECT MANAGEMENT |  |  |  |  | PROJECT MANAGEMENT
PROJECT MANAGER CONTENT DEVELOPER | PROJECT START INITIAL MEETING
PROJECT MANAGER CONTENT DEVELOPER DESIGNER | IDENTIFYING GOALS NEEDS ASSESSMENT PROJECT PLANNING
CONTENT DEVELOPER |  |  | CONTENT PLANNING
CONTENT DEVELOPER DESIGNER DEVELOPER |  |  |  |  | SITE OUTLINE | SITE STRUCTURE
DESIGNER | [7 empty] | STYLE TILES |  |  | WIREFRAMES
CONTENT DEVELOPER COPYRIGHTER | [7 empty] | TEXT DEVELOPMENT
CONTENT DEVELOPER DESIGNER | [11 empty] | UI PLANNING AND TESTING |  |  |  | UI TESTING
DEVELOPER | [10 empty] | CODING, INTEGRATION AND SITE BUILD |  |  |  |  | CODING, INTEGRATION AND SITE BUILD
DEVELOPER | [16 empty] | CROSS PLATFORM BROWSSER TESTING
DEVELOPER | [17 empty] | VALIDATING
CONTENT DEVELOPER DESIGNER DEVELOPER | [18 empty] | REFINEMENT
PROJECT MANAGER CONTENT DEVELOPER DESIGNER DEVELOPER | [19 empty] | LAUNCH